## Slide 1: PPM # - Project Name
Month Date, Year
Project Overview | Gate 2 Approval
UFIT Project Management Office

## Slide 2: Project Overview
Project overview is intended to explain to the project sponsors and leadership the high-level understanding of what will be accomplished.

## Slide 3: Project Scope-Key Highlights
In Scope
Out of Scope
This document summarizes Scope items (products, services and results) and out of scope items related to the project.

## Slide 4: Project Scope-Key Highlights (Continued)
List here any unique products/services that can be verified or approved and are required to complete a process, phase or project.

## Slide 5: Project Budget and Resource Estimates
Name | Role | Month 1 (Total Hrs by Month) | Month 2 (Total Hrs by Month) | Total Hrs | Costs: avg of $63/hour
Resource Name | Role Name | 30 | 30 | 60 | $
Resource Name | Role Name | 10 | 10 | 20 | $
 |  |  | Total | 80 | $

## Slide 6: Core Office Budget and Resource Estimates
Name | Role | Month 1 (Total Hrs by Month) | Month 2 (Total Hrs by Month) | Total Hrs | Costs
Resource Name | Role Name | 30 | 30 | 60 | $
Resource Name | Role Name | 10 | 10 | 20 | $
 |  |  | Total | 80 | $
OPTIONAL in Gate 2 presentation

## Slide 7: Financial Considerations
(Replace text with information on consultant fees, software fees, additional FTEs and total cost of ownership (ex: new service ID owner and predicted costs outside of initial project).)
Name | Chart field Number | Fund (dept/fund admin)
Consultant Fees |  | 
Software Fees |  | 
Additional FTEs |  | 
Total Cost of Ownership |  | 

## Slide 8: Project Timeline
Jul
Aug
Sep
Fri 7.24
Today
Wed 8.26
92921 PeopleTools 8.57 Upgrade Execute in TST
Fri 8.21
92921 PeopleTools 8.57: Build QAT Region and Database work
92921 PeopleTools 8.57: Build TST Region and Database work
92921 PeopleTools 8.57 Upgrade Execute in QAT
Fri 9.25
QAT final sign off
Thu 9.24
PeopleTools 8.57 Project Deployment
Sat 9.26
ES Analysts/Dev Testing and Fixes in TST
4 weeks
07.27.20 - 08.21.20
ES Analyst/Dev Testing and Review in QAT
08.27.20 - 09.18.20
Load Testing (Advance Registration)
Deployment Checklist Meeting
09.21.20
08.27.20 - 09.18.20
3.4 weeks
3.4 weeks

## Slide 9: Considerations/Potential Risks
Type | Description | Impact | Mitigation
Risk OR consideration | The university campus community must be notified about the project and any business process modifications that might occur because of the upgrade. |  | Establish clear lines of communication between the project team and the customer Proactively manage communication Develop issue logs and plans to track and resolve issues Follow up on action items Ensure all project status information is accurate and up-to date
 | This project has an effect, and any issues could affect several functional areas and business processes. |  | Additional cycles of work will be needed to complete the work. Work on the processes with the iterative process with the functional teams to resolve issues.
 | Core office area resources must be allocated to work on this project and perform functional area testing within the project timelines. |  | Unable to deliver on the project timeline. Proactively work with the BRMs and Core Office to ensure backups are secured and timelines are communicated.
 | Security might be needed for the upgrade. |  | Effective testing and ongoing monitoring and evaluation can provide a level of confidence that security controls can adequately mitigate perceived risks.
 | During the upgrade, the project may need to apply fixes and patches to project environments such as production. |  | Effective change management processes and control handle patches in a planned, foreseeable means, subject to the similar analysis and process as any other changes.

## Slide 10: Own and Operate: Service Owner Deliverables
(Replace text with your project information.)
Service Ownership | Deliverable
UF Help Desk | Build FAQ’s and Just In Time Training for Supplier On/Off Boarding
Enterprise Systems – Finance – UFIT Application Support Service Owner: Lee Hinkle | Build FAQ’s, Job Aides, Instructor Lead, Online Training, and Quick Reference Guides for UF Departments
Enterprise Systems – Systems & Programming Services – UFIT PeopleSoft Development Service Owner: Nicole Jeffers | Train UF Computing Help Desk support workflow for Supplier Portal
 | Disaster Recovery Documentation

## Slide 11: Own and Operate: Service Owner Escalation
Service Ownership | Description
UF Help Desk | Campus Users Tier 1 Support
Enterprise Systems – Finance – UFIT Application Support Service Owner: Lee Hinkle | UFIT Application Support Tier 2 support
Enterprise Systems – Systems & Programming Services – UFIT PeopleSoft Development Service Owner: Nicole Jeffers | UFIT ERP Services Tier 3 support

## Slide 12: Project Benefits
Benefits
  Decrease documented vulnerabilities by 10%.
  Modernization of legacy systems.
  Adoption of new technologies and standards that will improve services and efficiency.
  Potential to improve business processes, including extraneous SQL, which runs during registration load events.
  Keeping current
  Improving customer experience – quantify

## Slide 13: Appendix – add hyperlinks to documents below
Project Charter
Project Scope
Project Workplan
Other relevant documents (Project Requirements Specification…)

## Slide 14: Sign Off